## Communication-Sheet
Communication | Audience | Goals | Schedule | Communication Type | Format | Responsibility
Kick-off meeting | All Project Stakeholders | • Introduce the project to stakeholders, • Manage expectations • Set expectations | TBD , one time event | Email , Google Doc , Google Sheets | • Meeting with SLA • Project Charter document • Presentation | Project Manager
Steeing Committee | Steering Committee, Project leads, Stakeholders(if required) | • Review Status • Manager Performance • Clear Issues | Weekly | Email | Meeting | Project Manager
Status Report | All Project Stakeholders | • Communicate current progress,issues and risks | Weekly, atleast 24 hours before the steering meeting | Email , Google Doc , Google Sheets | Report | Project Manager
Team Meeting | Project Team | • Report Status • Identify Issues • Develop resoultion as team | Weekly, atleast 24 hours before the status review is due | Email , Google Docs, Confluence | • Meeting • Project plan • Status report | Project Manager
Team Standups | Development & QA Team | • Coordinate work for the day • Track status of each tasks • Evaluate project timeline | Start of each business day | Jira | Timeboxed standup meet within 15 min | Project Manager
MileStrone Review | All Project Stakeholders | • Review Status • Present Deliverables • Gather Feedback • Decide on next steps | At project milestone | Email, Confluence | Meeting , review or demonstration of deliverables | Project Manager
Lesson Learned | Project Team | • Review Success • Capture failure and document for future • Discuss scope for improvement • Appreciate/Kudos to team | At project end | Email, Confluence | Meeting that produces lesson learned document | Project Manager