## SLA Register
Project Name : | Park Reservation Kiosk |  |  |  | Date | 2021-06-23
Project Phase : | Phase-1
Name of the Stakeholder | Designation | Department | Role in Project | Type of Stakeholder | Type of Communication | Expectations | Interests | Influence on Project Outcome
Brandon McKey | Chief Federal Communnication Engineer | Federal Communication Commission | Internet Service Provider | External | Weekly Video Conference and Weekly Status Email | Mesurable Business Success On-Time Delivery | Keep Informed | Influencer
James Swift | Park Administrator | National Park Range Department | Park Onsite field officer | External | Montly Video Conference | Reliable and less maintabable Kiosk machine | Monitor | Supporter
Peter Park | Kiosk Vendor | Regional Kiosk Team | Support and Maintanence of Kiosk | External | Montly Video Conference | Resolve issues Reliable Business Success | Closely Monitor | Supporter
Craig Law | Product Owner | Operations Team | Design Product Requirement Document | Internal | Daily Standups Weekly sync and Email udpates | Complete project on time | Manage Closely | Influencer
Kevin Reed | Architect | UI Team | Design the architecture model | Internal | Daily Standups Weekly sync and Email udpates | Complete project on time with best reliable design | Manage Closely | Influencer
Micheal Hussey | Quality Engineer | QA Team | Develop test cases | Internal | Daily Standups Weekly sync and Email udpates | Complete project on time with best quality testing | Closely Monitor | Supporter