## Details
ABC Development Project
|  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Project | Rate Per Hour | Work Package | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Hrs | Overhead Cost Per Month | Management Reserve | Annual Training Forecast | Contingency Reserve
Other Costs | [26 empty] | 1250500 | 250000 | 2100100
Task A.1
Resources:
Bill L. | 65 | 1.1.1 | 20 | 25 | 25 | 25 | 30 | 25 | 35 | 25 | 40 | 25 | 45 | 25 | 50 | 25 | 47 | 25 | 44 | 25 | 41 | 25 | 38 | 25 | 35 | 25 | 29250 | 300
Jim K. | 72 | 1.1.1 | 25 | 25 | 29 | 25 | 33 | 25 | 37 | 25 | 41 | 25 | 45 | 25 | 49 | 25 | 46 | 25 | 43 | 25 | 40 | 25 | 37 | 25 | 34 | 25 | 33048 | 300
Don W. | 58 | 1.1.1 | 15 | 25 | 21 | 25 | 27 | 25 | 33 | 25 | 39 | 25 | 45 | 25 | 51 | 25 | 48 | 25 | 45 | 25 | 42 | 25 | 39 | 25 | 36 | 25 | 25578 | 300
Eric Z. | 81 | 1.1.1 | 45 | 25 | 52 | 25 | 59 | 25 | 66 | 25 | 73 | 25 | 80 | 25 | 87 | 25 | 84 | 25 | 81 | 25 | 78 | 25 | 75 | 25 | 72 | 25 | 69012 | 300
Task A.2
Gloria B. | 68 | 1.2.1 | 23 | 25 | 28 | 25 | 33 | 25 | 38 | 25 | 43 | 25 | 48 | 25 | 53 | 25 | 50 | 25 | 47 | 25 | 44 | 25 | 41 | 25 | 38 | 25 | 33048 | 300
Sam S. | 65 | 1.2.1 | 29 | 25 | 33 | 25 | 37 | 25 | 41 | 25 | 45 | 25 | 49 | 25 | 53 | 25 | 50 | 25 | 47 | 25 | 44 | 25 | 41 | 25 | 38 | 25 | 32955 | 300
Derick B. | 71 | 1.2.1 | 19 | 31 | 25 | 31 | 31 | 31 | 37 | 31 | 43 | 31 | 49 | 31 | 55 | 31 | 52 | 31 | 49 | 31 | 46 | 31 | 43 | 31 | 40 | 31 | 34719 | 372
Task A.3
Cindy L. | 92 | 1.3.1 | 33 | 23 | 39 | 23 | 45 | 23 | 51 | 23 | 57 | 23 | 63 | 23 | 69 | 23 | 66 | 23 | 63 | 23 | 60 | 23 | 57 | 23 | 54 | 23 | 60444 | 276
Marty B. | 84 | 1.3.1 | 44 | 25 | 50 | 25 | 56 | 25 | 62 | 25 | 68 | 25 | 74 | 25 | 80 | 25 | 77 | 25 | 74 | 25 | 71 | 25 | 68 | 25 | 65 | 25 | 66276 | 300
Larry B. | 66 | 1.3.1 | 26 | 25 | 32 | 25 | 38 | 25 | 44 | 25 | 50 | 25 | 56 | 25 | 62 | 25 | 59 | 25 | 56 | 25 | 53 | 25 | 50 | 25 | 47 | 25 | 37818 | 300
Jon W. | 95 | 1.3.1 | 48 | 31 | 54 | 31 | 60 | 31 | 66 | 31 | 72 | 31 | 78 | 31 | 84 | 31 | 81 | 31 | 78 | 31 | 75 | 31 | 72 | 31 | 69 | 31 | 79515 | 372
Kim T. | 79 | 1.3.1 | 38 | 23 | 44 | 23 | 50 | 23 | 56 | 23 | 62 | 23 | 68 | 23 | 74 | 23 | 71 | 23 | 68 | 23 | 65 | 23 | 62 | 23 | 59 | 23 | 56643 | 276
[8 empty] | Calculate the Cost Baseline | [18 empty] | 558306 | 3696
[8 empty] | Cost Budget = Cost Baseline + Management Reserve | [9 empty] | 3536702
[8 empty] | Cost Baseline = Cost Estimate + Contingency Reserve | [9 empty] | 2286202
[8 empty] | Cost Estimate = sum of costs for work packages/activities | [9 empty] | 186102
[16 empty] | Total |  | 6009006
Calculated Cost Estimate
|  |  | Total Activities |  |  | 3 |  |  | Since 3 Tasks
|  |  | Total Work Package(Sum) |  |  | 558306 |  |  | Calculated from Column AB
|  |  | CostEstimate |  |  | 186102